🌿 ESCAPE WITHIN

6-Month Comprehensive Roadmap

From Idea to Movement

January 2026 → June 2026

OVERVIEW

| Phase | Months | Theme | Goal |
| --- | --- | --- | --- |
| Phase 1 — Build | Month 1 & 2 | Foundation | Set up everything before launch |
| Phase 2 — Launch | Month 3 & 4 | First Programs | Run first 2 retreats, build proof |
| Phase 3 — Grow | Month 5 & 6 | Scale & Expand | Systemise, grow community, increase revenue |

MONTH 1 — FOUNDATION

Build the base. Set up every system before anything goes public.

LEGAL & STRUCTURE

| Task | Action | Owner | Deadline |
| --- | --- | --- | --- |
| Entity Registration | Register Trust or Section 8 Company | Founder | Week 2 |
| Brand Trademark | File 'Escape Within' & 'Utter Feeling' | Legal Advisor | Week 3 |
| Art of Living NOC | Get written no-objection from mentor | Mentor Coordinator | Week 2 |
| Volunteer Agreement | Draft simple volunteer contract | Legal Advisor | Week 4 |
| Participant Waiver | Draft liability waiver for programs | Legal Advisor | Week 4 |
| Bank Account | Open dedicated current account | Finance & Admin | Week 3 |

TEAM BUILDING

| Role | Action | Target |
| --- | --- | --- |
| Core Team (6) | Send WhatsApp recruitment message | Week 1 |
| Sales Team (3) | Interview & onboard via Art of Living network | Week 2 |
| Mentor Coordinator | Confirm Art of Living mentor for Month 3 | Week 3 |
| All Volunteers | Share role descriptions & get commitments | Week 4 |

TECHNOLOGY SETUP

| Tool | Setup Action | Owner |
| --- | --- | --- |
| WhatsApp Business | Set up auto-reply, broadcast lists | Marketing Lead |
| Google Workspace | Shared Drive, Gmail, Calendar, Sheets | Tech / Admin |
| Notion | Set up team workspace, SOPs, checklists | Operations Manager |
| Razorpay | Set up payment links | Finance & Admin |
| Google Sheets CRM | Build Lead, Participant & Alumni sheets | Sales Lead |
| Canva Pro | Brand kit — colours, fonts, logo | Marketing Lead |
| Instagram Business | Set up page, bio, highlights | Marketing Lead |

MONTH 1 MILESTONES

✅  Entity registration initiated

✅  Core team of 13 confirmed

✅  All technology tools set up

✅  Art of Living NOC received

✅  Brand kit ready

✅  Razorpay payment link live

MONTH 2 — PREPARATION

Plan the first program. Start outreach. Build anticipation.

PROGRAM PLANNING

| Task | Action | Owner |
| --- | --- | --- |
| Select Month 3 Location | Scout & confirm venue — hills or nature resort | Operations Manager |
| Confirm Mentor | Lock Art of Living mentor for first retreat | Mentor Coordinator |
| Program Agenda | Draft 3-day session plan with mentor | Mentor Coordinator |
| Pricing | Set Standard, Premium & Volunteer seat prices | Founder |
| Transport Plan | Map pickup points & travel logistics | Operations Volunteer |
| Food & Stay | Confirm meals, accommodation, dietary needs | Hospitality Volunteer |

SALES & OUTREACH

| Activity | Target | Owner |
| --- | --- | --- |
| Personal WhatsApp outreach | Contact 200 people from Art of Living network | Sales Team |
| Mentor community outreach | Mentors share with their students | Mentor Coordinator |
| Daily follow-up calls | 10 calls per day per sales caller | Sales Callers |
| Corporate outreach | 5 companies pitched for group bookings | Community Outreach |
| Goal | 30 confirmed registrations for Month 3 program | Sales Lead |

MARKETING & CONTENT

| Content | Platform | Frequency |
| --- | --- | --- |
| Introduction post — What is Escape Within | Instagram | Week 1 |
| Mentor introduction reel | Instagram + WhatsApp | Week 2 |
| Location teaser post | Instagram | Week 3 |
| Testimonial from Art of Living experience | Instagram + WhatsApp | Week 3 |
| Program announcement post | Instagram + WhatsApp Broadcast | Week 4 |
| WhatsApp broadcast to full network | WhatsApp | Week 4 |

MONTH 2 MILESTONES

✅  First venue confirmed & deposit paid

✅  Mentor confirmed for Month 3

✅  30 registrations collected

✅  Instagram page live with 5 posts

✅  CRM populated with 100+ leads

✅  Program agenda finalised

MONTH 3 — FIRST PROGRAM

Run the first retreat. Capture everything. Build proof.

PRE-PROGRAM (Week 1 & 2)

| Task | Action | Owner |
| --- | --- | --- |
| Final headcount | Confirm all 30–40 participants | Sales Lead |
| Participant prep guide | Send via WhatsApp 7 days before | Admin |
| WhatsApp group | Create program-specific group | Ground Coordinator |
| Day-before reminder | Send location pin + packing list | Admin |
| Volunteer briefing | Conduct 1-hour briefing call with all volunteers | Operations Manager |
| Content plan | Plan what to capture each day | Content Volunteer |

DURING PROGRAM (Week 3)

| Day | Focus | Content to Capture |
| --- | --- | --- |
| Day 1 | Arrival, ice-breaking, evening session | Group arrival, first impressions, sunset |
| Day 2 | Full day — morning kriya, sessions, nature walk | Morning practice, candid moments, nature |
| Day 3 | Closing session, sharing circle, departure | Testimonial videos, group photo, tears & smiles |

POST-PROGRAM (Week 4)

| Task | Action | Timeline |
| --- | --- | --- |
| Testimonial collection | Send form & collect video testimonials | Within 48 hours |
| Alumni WhatsApp group | Move all participants to alumni group | Day 1 after program |
| Content creation | Edit reels, posts from program footage | Within 5 days |
| Post-program report | Document learnings, feedback, finances | Within 7 days |
| Month 4 announcement | Open registrations for next program | End of week 4 |
| Team debrief | What worked, what to improve | Within 3 days |

MONTH 3 MILESTONES

✅  First program successfully completed

✅  30–40 participants attended

✅  10+ video testimonials collected

✅  3 reels posted from program

✅  Alumni WhatsApp group created

✅  Month 4 registrations opened

MONTH 4 — BUILD MOMENTUM

Use proof from Month 3. Scale outreach. Run second program.

SALES & OUTREACH

| Activity | Target | Note |
| --- | --- | --- |
| Testimonial-led outreach | Share Month 3 videos to warm leads | Most powerful tool now |
| Alumni referrals | Ask every alumni to refer 2 people | Offer ₹500 discount per referral |
| Expand Art of Living reach | New chapters & cities contacted | Sales Team |
| Corporate group pitch | Target IT & finance companies | 5–10 seats per company |
| Registration goal | 40–50 confirmed for Month 4 program | Sales Lead |

MARKETING & CONTENT

| Content | Platform | Purpose |
| --- | --- | --- |
| Testimonial reels from Month 3 | Instagram + WhatsApp | Social proof |
| Behind the scenes content | Instagram Stories | Authenticity |
| Mentor Q&A reel | Instagram | Authority & trust |
| New location teaser | Instagram + WhatsApp | Anticipation |
| Alumni story feature | Instagram | Community feeling |
| Weekly WhatsApp broadcast | WhatsApp | Consistent touchpoint |

OPERATIONS

| Task | Action |
| --- | --- |
| New location | Coastal town or forest eco-resort |
| Systemise logistics | Create standard venue checklist from Month 3 learnings |
| Improve volunteer roles | Update briefing based on Month 3 feedback |
| Finance review | Review Month 3 P&L, adjust Month 4 pricing if needed |

MONTH 4 MILESTONES

✅  40–50 participants in Month 4 program

✅  Alumni community reaches 80+ people

✅  Instagram reaches 500+ followers

✅  First corporate group booking secured

✅  Operations SOP documented in Notion

MONTH 5 — SYSTEMISE & SCALE

Stop doing everything manually. Build systems that run without you.

AUTOMATION IMPLEMENTATION

| Area | Automation to Set Up | Tool |
| --- | --- | --- |
| Lead follow-up | Auto WhatsApp sequence on enquiry | WhatsApp Business |
| Payment confirmation | Auto receipt + welcome message | Razorpay |
| Pre-program comms | 7-day and 1-day auto reminders | WhatsApp Broadcast |
| Post-program | Auto testimonial request after program | WhatsApp Business |
| Content scheduling | 2 weeks of posts scheduled in advance | Meta Business Suite |
| CRM upgrade | Move to Zoho CRM from Google Sheets | Zoho CRM |

TEAM & VOLUNTEER EXPANSION

| Area | Action |
| --- | --- |
| Recruit city coordinators | 1 volunteer per city to drive local registrations |
| Sales team review | Assess performance, replace if needed |
| Mentor pool | Onboard 2nd Art of Living mentor as backup |
| Content team | Add 1 dedicated editor for reels |

REVENUE & FINANCE

| Area | Action |
| --- | --- |
| Premium tier launch | Introduce ₹18,000+ premium seats with added benefits |
| Early bird pricing | Offer discount for registrations 30 days in advance |
| Reserve fund | Maintain 20% of each program revenue as buffer |
| Break-even review | Confirm if movement is self-sustaining |

MONTH 5 MILESTONES

✅  Full automation loop running

✅  Zoho CRM live with all data migrated

✅  100+ alumni community

✅  Premium tier seats launched

✅  2 city coordinators onboarded

✅  Movement is financially break-even

MONTH 6 — FLAGSHIP & FUTURE

Run the most ambitious program. Plan Year 2. Celebrate the movement.

FLAGSHIP PROGRAM

| Element | Detail |
| --- | --- |
| Location | Himalayas or International — Bali / Nepal / Sri Lanka |
| Seats | Limited to 25 premium seats |
| Price | ₹25,000 to ₹45,000 inclusive |
| Mentor | Senior Art of Living teacher |
| Duration | 5 days (extended from standard 3 days |
| Content | Full documentary-style video production |
| Goal | Create the most powerful content asset for Year 2 launch |

COMMUNITY & ALUMNI

| Activity | Action |
| --- | --- |
| Alumni reunion event | Online or in-person gathering of all 150+ alumni |
| Community leadership | Identify 3–5 alumni as community ambassadors |
| Referral programme | Formalise referral rewards for alumni |
| Newsletter launch | Monthly Escape Within newsletter to all alumni |

YEAR 2 PLANNING

| Area | Plan |
| --- | --- |
| Locations | Expand to international every quarter |
| Team | Consider first paid role — Operations Manager |
| Revenue | Target ₹10–15L per program at scale |
| Brand | Launch Escape Within merchandise & app |
| Partnerships | Corporate wellness tie-ups, yoga brands |
| Media | Pitch to wellness magazines & podcasts |

MONTH 6 MILESTONES

✅  Flagship international or Himalayan program completed

✅  150+ total alumni across 6 programs

✅  Documentary reel produced

✅  Year 2 plan documented

✅  First paid team member onboarded

✅  Brand trademark confirmed

6-MONTH AT A GLANCE

| Month | Theme | Program | Participants | Key Milestone |
| --- | --- | --- | --- | --- |
| Month 1 | Foundation | No program — setup only | — | Team of 13 confirmed, all systems live |
| Month 2 | Preparation | No program — outreach only | — | 30 registrations collected, venue confirmed |
| Month 3 | First Program | Hills / Nature Retreat | 30–40 | First retreat done, testimonials collected |
| Month 4 | Momentum | Coastal / Forest Retreat | 40–50 | Alumni community 80+, first corporate booking |
| Month 5 | Scale | Temple Town / Spiritual Hub | 40–50 | Break-even, full automation running |
| Month 6 | Flagship | Himalayas / International | 20–25 | 150+ alumni, Year 2 plan ready |

6-MONTH FINANCIAL PROJECTION

| Month | Revenue (Est.) | Expenses (Est.) | Net |
| --- | --- | --- | --- |
| Month 1 | ₹0 | ₹15,000 (setup) | -₹15,000 |
| Month 2 | ₹0 | ₹20,000 (venue deposit, ads) | -₹20,000 |
| Month 3 | ₹3,00,000 | ₹1,80,000 | +₹1,20,000 |
| Month 4 | ₹4,00,000 | ₹2,00,000 | +₹2,00,000 |
| Month 5 | ₹4,50,000 | ₹2,20,000 | +₹2,30,000 |
| Month 6 | ₹6,00,000 | ₹3,00,000 | +₹3,00,000 |
| TOTAL | ₹17,50,000 | ₹8,35,000 | +₹9,15,000 |

Stillness is not something you create —

it is what remains when everything else falls away.

🌿 Escape Within — Go Still. Come Alive.